## Product Backlog
ID | User Story
1 | As a user i should be able to sign in.
2 | As a user i should be able to view all course/staff schedule.
3 | As a User I should be able to view the bus schedule.
4 | As a student i should be able to view schedules.
5 | As a TA is should be able to view the exact hours spent in the university and the remaining hours
6 | As a student/doc/TA I should be able to see calender
7 | As a TA, i ahould be able to view my proctoring schedule.
8 | As a student, I should get notified about my tutorial
9 | As a TA/Doctor I should be able to post the compensation slots on the system
10 | As a TA i should be able to manage tutorial attendance
11 | As a student, I should be able to post questions after every lecture in the courses I take.
12 | As a doctor, I should review the students' questions after each lecture.
13 | as a student I should be able to view staff's member info
14 | As a student I should be able to switch my tutorial group
15 | As a student, I should be able to reserve (request) office hours
16 | As a TA, I should be able to (accept/ reject) a office hour request
17 | As a student I should be able to keep up with my progress in University.
18 | As a TA, i should be able to assign the progress of the questions i marked in the midterm/final exams.
19 | As a Dr , i should assign the questions that i will mark in the midterm/final exams.
20 | As a TA i should be able to enter students' grades for assigments/projects/ quizzes
21 | As a TA i should be able to enter students' grades for FINALS AND MID
22 | As Dr/TA I should be able to view grades progress of the students
23 | As a doctor, i should be able to know the exam locations of the courses i teach
24 | As a doctor, I should be able to see how many students took my exam.
25 | As a Doctor, i should choose the maximum number of students to supervise on.
26 | A a doctor I should be able to view the TAs that teach my course.
27 | As a DR is should be able to post deadlines.
28 | as a student/TA I should be able to reserve a room.
29 | As a Student I should be able to request after hours permission
30 | As a student I should be able to evaluate courses and academics
31 | As a Doctor i should be able to view evaluation of the students for my course
32 | As a researcher I should be able to evaluate my supervisor.
33 | As a researcher I should be able to view my supervisor's evaluation of me.
34 | As a student ,i should be able to reserve a Make up exam
35 | As a student i should be able to submit final exam excuses
36 | As a Student I should be able to reserve a German placement test on system
37 | As a student i should be able to reserve summer course
38 | As a Student i should be able to access avalible internal internships on the system
39 | as a student I should be able to know about my internships
40 | As a student I should be able to view prerequisite courses for every course.
41 | As a student I should be able to add/drop the courses in a semester.
42 | As a TA I should be able to pick the courses I want to teach next semester.
43 | As a student I should be able to declare my major.
44 | As a student/resaercher, i should be able to reserve the theses topics that i want that a doctor posted.
45 | As a researcher , i should be able to communicate with my supervisor
46 | As a researcher I should be able to find materials for my masters
47 | As a researcher , I should be able to make requests
48 | As a researcher I should be notified of any coming meetings with my supervisor.
49 | As a researcher, i should be able to submit my progress to the postgraduste office.
50 | As a student, I should apply to be one of the curriculum committe students.
51 | As a student, I should be able to view events taking place at university.
52 | As a user i should be able to resrve parking slot.

## Sprint 1 Backlog
ID | User Story | Team Member | Story points | Reason
1 | As a user i should be able to sign in. | Maryam | 2 | It is the simplest task but it needs a sign in for different users and
2 | As a user i should be able to view all course/staff schedule. | Maryam | 3 | It requires many permutations and constraints to fully complete the testing cases
3 | As a User I should be able to view the bus schedule. | Sarah | 2 | It will need the Schedule for alll buses and should be updated once a week incase of any changes
4 | As a student I should be able to view schedules. | Arwa | 5 | Schedules means different schedules for exam, tutorial and summer .
5 | As a TA is should I be able to view the exact hours spent in the university and the remaining hours | Donia | 1 | It requires a small database to save the working hours for each TA and to show it only needs one layer that represent those hours
6 | As a student/doc/TA I should be able to see calender | Sarah | 1 | it is a simple task because the calender will just be uploaded once for each semester for the TAs,Students and Doctors to see
7 | As a TA, i should be able to view my proctoring schedule. | Maryam | 3 | Each TA would have his own Schedule updated in each exam time
8 | As a student, I should get notified about my tutorial | Dalia | 5 | it should work for each slot and each student and needs many layers to represent the tutorial info and place
9 | As a TA/Doctor I should be able to post the compensation slots on the system | Maryam | 5 | It should show the DR/TA the updated schedule for the compensation student and then it should check for the reserved rooms
10 | As a TA i should be able to manage tutorial attendance | Donia | 5 | managing attendance needs buttons for each name and different layers for each tutorial
11 | As a student, I should be able to post questions after every lecture in the courses I take. | Reem | 5 | It needs many Layers to represent different lectures a day and it should save the questions for all students in the slot

## Sprint 2 Backlog
ID | User Story | Team Member | Story points | Reason
12 | As a doctor, I should review the students' questions after each lecture. | Dalia | 2 | Since the retrieval of the questions from the database will be a simple query and display them will be very easy.
13 | as a student I should be able to view staff's member info | Arwa | 1 | Since the query retrieval of it needs only one table and a simple condition
14 | As a student I should be able to switch my tutorial group | Donia | 5 | Since it has request and response to switch and to show who is the requester and their schedule, and also to be notified about any requests.
15 | As a student, I should be able to reserve (request) office hours | Sarah | 3 | it should show the TA/Dr office hours to choose from and then send a notification for the TA
16 | As a TA, I should be able to (accept/ reject) a office hour request | Reem | 2 | it should only show the TA the office hours notification so that he/she could accept it or noy
17 | As a student I should be able to keep up with my progress in University. | Maryam | 8 | it should show the student his grades in quizzes, finals , midterms and his/her transcript
18 | As a TA, i should be able to assign the progress of the questions i marked in the midterm/final exams. | Donia | 2 | The assigment of a new data in the database with simple conditions is not a difficult task.
19 | As a Dr , i should assign the questions that i will mark in the midterm/final exams. | Reem | 3 | To assign questions to every TA requires multiple tables which requires some work.

## Sprint 3 Backlog
ID | User Story | Team Member | Story points | Reason
20 | As a TA i should be able to enter students' grades for assigments/projects/ quizzes | Dalia | 8 | it needs many layers to allow the TA to post the grades for all the course work
21 | As a TA i should be able to enter students' grades for FINALS AND MID | Arwa | 5 | only TAs who corrected those exams should be allowed and it should show an easy mockup to ease entering grades and showing them so that a Dr/TA can double check befor submitting them
22 | As Dr/TA I should be able to view grades progress of the students | Reem | 3 | it should be updated each semester and shoul show grades using two ways statistics and individual and it shoul be seperated for each major
23 | As a doctor, i should be able to know the exam locations of the courses i teach | Donia | 2 | it should show each exam timing and location for each group or tutorial
24 | As a doctor, I should be able to see how many students took my exam. | Sarah | 3 | After each exam the people who took should be counted and the result should be posted for the subject's doctor only
25 | As a Doctor, i should choose the maximum number of students to supervise on. | Maryam | 1 | each doctor should post the number of students to supervise on a simple task that only needs a doctor to submit a number of students

## Sprint 4 Backlog
ID | User Story | Team Member | Story points | Reason
26 | A a doctor I should be able to view the TAs that teach my course. | Donia | 1 | It is a simple task to get the TAs who teach a specific course and requires only one table.
27 | As a DR is should be able to post deadlines. | Donia | 1 | It is simple as it needs only setting the information needed about the deadline with its specified course in a sing;e table in the database.
28 | as a student/TA I should be able to reserve a room. | Reem | 5 | It is not easy to retireve all the rooms in the university and it is available or not in a specific time as it requires many tables and much work in the frontend.
29 | As a Student I should be able to request after hours permission | Donia | 1 | It is easy to save the informatin needed to request after hours permission and it has a simple task in the frontend.
30 | As a student I should be able to evaluate courses and academics | Reem | 3 | The courses/staff taken should be retrived and questions shown, and then save the evaluation responses in the database.
31 | As a Doctor i should be able to view evaluation of the students for my course | Donia | 2 | It is not simple to retrieve the evaluation of all the students throughout the semester and calculate and show the average of the answers of each question.
32 | As a researcher I should be able to evaluate my supervisor. | Arwa | 1 | It is an easy task since it only saves the evaluation of only one supervisor.
33 | As a researcher I should be able to view my supervisor's evaluation of me. | Arwa | 1 | It is an easy task since it only views the evaluation of only one supervisor.
34 | As a student ,i should be able to reserve a Make up exam | Arwa | 5 | It is not simple to retrieve the courses taken in the current semester and if it is able to reserve one or not.
35 | As a student i should be able to submit final exam excuses | Dalia | 3 | It is slightly simple to take retrieve the exam taken from the course and submit a final excuse as it needs only two tables from the database for getting the exams and setting the excuse.
36 | As a Student I should be able to reserve a German placement test on system | Dalia | 1 | It is easy to get the timing available and choosing one of them.
37 | As a student i should be able to reserve summer course | Dalia | 5 | It is not easy to retrieve the available summer courses and check if the student is able to apply for it or not.
38 | As a Student i should be able to access available internal internships on the system | Sarah | 1 | It is very easy as it requires the informations from only one table.
39 | as a student I should be able to know about my internships | Dalia | 1 | It is simple as it needs only one table to get the internships done till now.
40 | As a student I should be able to view prerequisite courses for every course. | Sarah | 1 | It needs only one relation (table) with one condition to get the prerequisite courses of a specific course.
41 | As a student I should be able to add/drop the courses in a semester. | Sarah | 8 | It needs the user to specify if the student will add/drop a course and after choosing the course, check will be done if the student is allowed to add/drop it or not.
42 | As a TA I should be able to pick the courses I want to teach next semester. | Maryam | 2 | it is a moderate task that should show info and summary for each course available and ask for a 1st and 2nd preference from the TA
43 | As a student I should be able to declare my major. | Maryam | 1 | It is an easy task that should be available only when the student is allowed to choose a major , and should only ask for his selection and post it
44 | As a student/researcher, i should be able to reserve the theses topics that i want that a doctor posted. | Maryam | 3 | it should ask for a topic from the student and should check for its relativity to the majors available

## Sprint 5 Backlog
ID | User Story | Team Member | Story points | Reason
45 | As a researcher , i should be able to communicate with my supervisor | Arwa | 2 | both the researcher email and Doctor email should be linked to a chat room to allow them tocommunicate
46 | As a researcher I should be able to find materials for my masters | Dalia | 3 | It needs links from different libraries free and bought and it should allow downloading those materials
47 | As a researcher , I should be able to make requests | Sarah | 2 | It should take a request for a resource or funding and a reason from the researcher to make sure about its importance
48 | As a researcher I should be notified of any coming meetings with my supervisor. | Donia | 1 | it should show the timing and slot and confirm meetings from researchers
49 | As a researcher, i should be able to submit my progress to the postgraduste office. | Donia | 1 | it should allow the user to upload his/her documents to be revised by Examination office
50 | As a student, I should apply to be one of the curriculum committe students. | Reem | 1 | it is an easy task that should work at the beginning of each semester to allow students to apply
51 | As a student, I should be able to view events taking place at university. | Reem | 1 | it is an easy task , every time an event is upcoming a poster for its timing and location should be posted
52 | As a user i should be able to resrve parking slot | Maryam | 3 | it is a task that require the system to keep up with the reservation for each parking slot and should show all slots available for the user